# Tritium DC Charger Inventory: Readiness Assessment

What is owned, what is evidenced, and what is required before deployment

# Position

UnyKorn LLC owns 50 Tritium-class DC fast chargers outright, paid in full. They are held in a third-party warehouse in Tennessee. None are installed and none are energised. The Norcross depot has 12 charging bays designed; none are built.

# Inventory

Units owned: 50 - Tritium-class DC fast chargers, paid in full

Nameplate: 75 kW - RTM75 believed; operator recalled ~85 kW - unconfirmed

Book value: $1.5M - $30,000 per unit; no independent appraisal yet

Location: Tennessee - Third-party warehouse; street address to be evidenced

Installed: None - No unit is energised at any site

# Evidence status

Bill of sale / invoices for all 50 units: Not yet provided

UCC lien search on UnyKorn LLC: Not yet run

Serial and model schedule with nameplate photos: Not yet provided

Warehouse receipt / bailee letter: Not yet provided

Inventory insurance certificate: Not yet provided

Manufacturer support letter (Exicom): Not yet requested

Independent appraisal - FMV and OLV: Not yet commissioned

Depot site control documentation: Not yet provided

# Critical path

1. Serial and model schedule with nameplate photographs - settles 75 kW vs ~85 kW and the NACS cable set, and is required before an appraiser will quote.

2. Written support letter from Exicom (acquired Tritium August 2024, retained the Lebanon TN factory) confirming warranty, firmware and service for these serial numbers.

# What this memo does not claim

No appraised value is claimed. No lien-free status is claimed. No charging revenue is claimed.

UnyKorn Black is operated by UnyKorn LLC. Not affiliated with, endorsed by or sponsored by Tesla, Inc. Nothing in this document is an offer to sell, or a solicitation of an offer to buy, any security or token. Figures are models, not forecasts or guarantees.